Work plan

Deadlines

2015-03-02 Choose a project proposal and send the result via email to epsatisep@gmail.com

2015-03-11 Define the Tasks (what must be done), Task allocation (who does what) and Gantt chart (when) of the project and insert them on the wiki (planning)

2015-03-27 Specify the list of material (what, quantity, where to buy - local companies are mandatory) on the wiki

2015-04-05 Upload the Interim Report and Presentation to the wiki; the report should contain the Introduction, including the tasks, team members allocation and Gantt chart, State of the Art, Marketing Plan, Project Management, Eco-eficiency Measures for Sustainability, Ethical and Deontological Concerns, Proposed Solution and Bibliography chapters

2015-04-09 Interim Presentation, Discussion and Assessment

2015-06-12 Upload the Final Report, Presentation, Video, Paper, Poster and Manual

2015-06-18 Final Presentation, Individual Discussion and Assessment

2015-06-25:

Update the wiki with all correction suggestions

Hand in a CD with the corrected deliverables (source + PDF) together with all code produced to the EPS coordinator

Hand in one printed exemplar of the corrected report to the EPS coordinator

2015-06-26:

Hand in the prototype and user manual to the client

Receive the EPS@ISEP certificate

Tasks

Task	Responsible
meetings	all
plannings	all
research
material	Paloma
technologies	Bartek, Eughan
identity	Anthony
life-cycle	all
requirements	all
target	all
brief
identity	Anthony
objectives	all
implementation
marketing	Carina
materials	Paloma, Eughan, Bartek
programming	Eughan, Bartek
construction	Paloma, Carina
safety	all
testing/controlling
distribution
internet	Anthony, Carina, Kristjan
marketing	Carina

Gantt Chart

WEEK 22/06/2015 - 26/06/2015 GANTT CHART