## Sheet1
Communication Type | Objective of Communication | Medium | Frequency | Audience | Owner | Deliverable | Format
Kickoff Meeting | Introduce the project team and the project. Review project objectives and management approach. | - Face to Face | Once | - Project Sponsor | Project Manager | - Agenda | Soft copy archived on team-3 wiki.
|  |  |  | - Project Team |  | - Meeting Minutes
- Stakeholders
Project Team Meetings | Review status of the project with the team. | Face to Face | As Needed | - Project Team | Project Manager | - Agenda | Soft copy archived on team-3 wiki.
- Meeting Minutes
- Project Schedule
Technical Design Meetings | Discuss and develop technical design solutions for the project. | Face to Face | As Needed | - Project Technical Staff | Technical Lead | - Agenda | Soft copy archived on team-3 wiki.
- Meeting Minutes
Weekly Project Status Meetings | Report on the status of the project to management. | Face to Face | Weekly | Project team Project sponsor | Project Manager | - Slide Updates - Project Schedule | Soft copy archived on team-3 wiki.
Project Status Reports | Report the status of the project including activities, progress, costs and issues. | Face to Face | Weekly | Project Sponsor | Project Manager | - Project Status Report | Soft copy archived on team-3 wiki.
|  |  |  | Project Team |  | - Project Schedule
Stakeholders
PMO